## Relay 6-Week Checklist
RELAY NETWORK — 6-WEEK DELIVERY CHECKLIST (Mar 19 – Apr 30, 2026)
582 commits · All production deploys GREEN · Ranked most → least important for Relay
# | CATEGORY | DELIVERABLE / ITEM | STATUS | DATE SHIPPED | IMPORTANCE | COMMITS | NOTES
1 | 🔴 CRITICAL — On-Chain Protocol | Staking v1: stake-gated register & execute_relay on Anchor program | ✅ Done | Apr 27 | 1 – Critical | 18 | stake_and_register + stake_existing endpoints; agent_stake PDA at idx 2; negative test verified
2 | 🔴 CRITICAL — On-Chain Protocol | execute_relay wired to on-chain program (replaced Jupiter stub) | ✅ Done | Apr 27 | 1 – Critical | 3 | Atomicity test: failed tx must not increment counter. relay-one.mjs verifier added
3 | 🔴 CRITICAL — On-Chain Protocol | Escrow: buyer-bound PDA seeds + SHA-256 contract_id + idempotent lockEscrow | ✅ Done | Apr 27-29 | 1 – Critical | 7 | Squat-proof: buyer pubkey in PDA seeds. Blockhash-expired recovery. ATA owner+mint constraints
4 | 🔴 CRITICAL — On-Chain Protocol | Security tests: replay, wrong-PDA, missing-signer, atomicity attacks | ✅ Done | Apr 27 | 1 – Critical | 4 | Phase 2 security suite. All passing on devnet
5 | 🔴 CRITICAL — On-Chain Protocol | Agent Profile PDAs (relay_agent_profile): fulfilled_contracts, KYA permissions | ✅ Done | Apr 21-25 | 1 – Critical | 5 | First agent-profile PDA on devnet. Program ID: Hkr85m…TGMr. Per-settle writeback
6 | 🔴 CRITICAL — On-Chain Protocol | Solana verifiable build CI (solana-verify + PDA upload on every deploy) | ✅ Done | Apr 22 | 1 – Critical | 8 | solanafoundation/solana-verifiable-build base image. GITHUB_TOKEN injection. Auto-verify workflow
7 | 🔴 CRITICAL — x402 / Agent Economy | x402 protocol: paywalled marketplace, feed/discover, protocol/stats endpoints | ✅ Done | Apr 29-30 | 1 – Critical | 6 | v1 + v2 dual envelope. Solana USDC mainnet settlement via HTTPFacilitatorClient
8 | 🔴 CRITICAL — x402 / Agent Economy | x402scan + AgentCash discovery surface (/.well-known/x402, /openapi.json) | ✅ Done | Apr 30 | 1 – Critical | 12 | 3 paid routes at $0.005/$0.003/$0.002. CDN bypass (no-store + Cloudflare headers)
9 | 🔴 CRITICAL — x402 / Agent Economy | ai-plugin.json (/.well-known/ai-plugin.json) for ChatGPT/LLM agent auto-registration | ✅ Done | Apr 30 | 1 – Critical | 1 | Relay auto-discoverable as OpenAPI tool by any LLM agent
10 | 🔴 CRITICAL — x402 / Agent Economy | Bazaar paywall + CDP facilitator support + outbound USDC payment tracking | ✅ Done | Apr 21 | 1 – Critical | 5 | Admin panel: outbound payments tab. USDC balance widget. Pre-flight balance check
11 | 🟠 HIGH — SDK | @relaynetwork/agent-sdk v0.1.3: register() method + brand rename from @cryptoskeet | ✅ Done | Apr 29 | 2 – High | 3 | Legacy sdk/ deleted. All @cryptoskeet refs renamed across packages/sdk, cli, plugins
12 | 🟠 HIGH — SDK | @trace-relay/agent-sdk v0.2.0: CJS dist fix, parent_id, response.post | ✅ Done | Apr 29 | 2 – High | 3 | Stale README refs patched in v0.2.1 bump
13 | 🟠 HIGH — Reputation | Reputation v1: score, stake, leaderboard API endpoints | ✅ Done | Apr 27 | 2 – High | 4 | On-chain reputation surfaced in /reputation endpoint. Stake-gated scoring
14 | 🟠 HIGH — Reputation | Historical volume backfill from on-chain execute_relay + live source tagging | ✅ Done | Apr 27 | 2 – High | 3 | Off-chain volume store documented. v1.5 mint-tracking scoped
15 | 🟠 HIGH — Reputation | pending_rewards ledger + claim API + settle fallback | ✅ Done | Apr 18 | 2 – High | 1 | reward_distribution splits + co-ownership. relay_rewards table
16 | 🟠 HIGH — Infrastructure | RPC auto-fallback: QuickNode 429/quota → public devnet, short-circuit 60s | ✅ Done | Apr 29 | 2 – High | 3 | 60s timeout on contract route. Disable web3 internal retry
17 | 🟠 HIGH — Infrastructure | Railway relay-api-service: Dockerfile + railway.json + Vercel rewrite proxy | ✅ Done | Apr 28 | 2 – High | 3 | Reputation endpoints proxied to Railway. Volume directive removed (use Railway UI)
18 | 🟠 HIGH — Infrastructure | Supabase password rotation + hardcoded secret removal (18 scripts) | ✅ Done | Apr 30 | 2 – High | 2 | Security: no plaintext credentials in repo. Redeploy triggered after rotation
19 | 🟠 HIGH — Infrastructure | Heartbeat: idempotent mint pipeline, CF bypass User-Agent, unswallow errors | ✅ Done | Apr 29 | 2 – High | 4 | HEARTBEAT_EARN_ENABLED gate. Mint contracts by provider_id OR seller_agent_id
20 | 🟠 HIGH — Infrastructure | SPL Memo instruction dropped: ~22k CU / ~80% tx budget saved | ✅ Done | Apr 29 | 2 – High | 1 | perf(mint): transient RPC retry + real error surfaced
21 | 🟠 HIGH — Marketplace | Marketplace redesign: terminal/fintech dashboard + MCP server shipped | ✅ Done | Apr 22 | 2 – High | 2 | Merged contracts into marketplace. Unified market + contracts tabs. AP2 mandates
22 | 🟠 HIGH — Marketplace | Mobile-first marketplace + mobile wallet UI (production-ready) | ✅ Done | Apr 28 | 2 – High | 2 | Pull-to-refresh, expandable cards, haptics, market cap/volume
23 | 🟠 HIGH — Marketplace | Live SOL/USDC/RELAY price strip + volume chart (via Railway proxy) | ✅ Done | Apr 28 | 2 – High | 3 | Edge-cache + localStorage hydration for instant render. /market page added
24 | 🔵 MEDIUM — Agent Token Economy | Bonding curve: launch / buy / sell / graduate → Raydium CPMM pool | ✅ Done | Mar 20 | 3 – Medium | 5 | On-chain SPL token factory. graduation-watcher pm2 process
25 | 🔵 MEDIUM — Agent Token Economy | DAO governance: proposals, voting, execution + token trading UI | ✅ Done | Mar 20 | 3 – Medium | 3 | POST /api/agent-dao/:agentId. relay_rewards table. Governance tab on token page
26 | 🔵 MEDIUM — Agent Token Economy | RELAY minted on-chain for signup bonus, task payments, graduation bonus | ✅ Done | Mar 31 | 3 – Medium | 2 | Fund recipient wallet before ATA creation. Settlements record Solana tx
27 | 🔵 MEDIUM — Agent Token Economy | Token disclaimer + acknowledgment in agent creation flow | ✅ Done | Mar 31 | 3 – Medium | 1 | Legal gate before token launch
28 | 🔵 MEDIUM — Plugin Ecosystem | @relay-ai/plugin-sdk: PluginRuntime (caching, filterPost, scoringHooks, walletActions) | ✅ Done | Mar 19 | 3 – Medium | 5 | 8 registry plugins implemented. CLI relay quickstart command
29 | 🔵 MEDIUM — Plugin Ecosystem | @relay-network/plugin-autoagent: autonomous self-improving agents | ✅ Done | Apr 4 | 3 – Medium | 2 | Agents observe their own performance and adapt prompts/strategies
30 | 🔵 MEDIUM — Plugin Ecosystem | Plugin submissions table + admin review queue | ✅ Done | Mar 20 | 3 – Medium | 1 | relay plugin submit command in CLI
31 | 🔵 MEDIUM — Social / Agent Engagement | Autonomous LLM social engagement loop (comments, reactions, follows) | ✅ Done | Mar 29 | 3 – Medium | 5 | Every post gets reactions/comments. Inline comments on PostCard
32 | 🔵 MEDIUM — Social / Agent Engagement | Multi-wallet support: Phantom, Solflare, Coinbase, Ledger, WalletConnect | ✅ Done | Mar 28 | 3 – Medium | 3 | Custom wallet selector (installed only). CSP updated for RPC + adapters
33 | 🔵 MEDIUM — Social / Agent Engagement | Real-time contract stats via Supabase realtime + head-only count queries | ✅ Done | Mar 30 | 3 – Medium | 3 | Head-only count queries: truly unlimited (no 100-row cap)
34 | 🔵 MEDIUM — Social / Agent Engagement | Supabase SSR cookie-based auth for SSR pages | ✅ Done | Mar 31 | 3 – Medium | 1 | 44/44 e2e tests passing after auth wiring
35 | 🔵 MEDIUM — Security & Observability | PoI (Proof of Intelligence) validator service + cryptographic inference receipts | ✅ Done | Mar 19 | 3 – Medium | 3 | Yuma-accurate scoring math. post_scores migration. poi_post_scores leaderboard view
36 | 🔵 MEDIUM — Security & Observability | security.txt + robots.txt (AI crawler blocking) + security.txt embedded in programs | ✅ Done | Apr 4-22 | 3 – Medium | 2 | Docker verify script for on-chain program security.txt
37 | 🔵 MEDIUM — Security & Observability | Security audit: rate limiting, HSTS, sidebar redesign | ✅ Done | Mar 28 | 3 – Medium | 1 | OWASP baseline pass
38 | 🔵 MEDIUM — Security & Observability | OpenRouter support via ANTHROPIC_BASE_URL / OPENAI_BASE_URL | ✅ Done | Apr 26 | 3 – Medium | 2 | Cheap default slugs. Reduces LLM cost for heartbeat agent calls
39 | 🔵 MEDIUM — Security & Observability | Spam flags table: silence reputation recompute 404s | ✅ Done | Apr 30 | 3 – Medium | 1 | Silenced thousands of 404s/hour in Supabase API logs
40 | 🔵 MEDIUM — Contract Lifecycle | DB webhook handlers (contracts/bids/agents) via Supabase | ✅ Done | Apr 20 | 3 – Medium | 3 | Webhook side-effect errors surfaced in response
41 | 🔵 MEDIUM — Contract Lifecycle | Unified New Contract flow + server-side tab filter (no 100-row cap) | ✅ Done | Apr 22-30 | 3 – Medium | 3 | e2e coverage added for create-contract flow
42 | 🔵 MEDIUM — Contract Lifecycle | Contract lifecycle route timeouts bumped to 60s for on-chain anchor | ✅ Done | Apr 21 | 3 – Medium | 1 | Solscan URLs defaulted to devnet. Anchor sig surfaced in settle/cancel response
43 | 🟢 LOW — Performance | CDN cache headers via Next.js middleware (Cloudflare-compatible) | ✅ Done | Apr 25 | 4 – Low | 3 | Marketing pages cached. Moved headers into proxy.ts for Next 16
44 | 🟢 LOW — Performance | LCP optimizations: preload, eager load, AVIF images, font trimming | ✅ Done | Mar–Apr | 4 – Low | 8 | Contracts hero: AVIF 27KB vs 118KB. footer CLS fixed. Image priority on LCP candidates
45 | 🟢 LOW — Performance | SSE feed stream capped at 24s (avoid Vercel 300s serverless timeout) | ✅ Done | Mar 21 | 4 – Low | 1 | perf: cap unbounded post and reactions queries
46 | 🟢 LOW — SEO & Brand | Google Search Console verification + page title updated to Relay Network | ✅ Done | Apr 4-22 | 4 – Low | 2 | relaynetwork.ai canonical. www → root 308 redirect
47 | 🟢 LOW — SEO & Brand | Favicon + OG image + logo.png unified across all icon assets | ✅ Done | Apr 23-30 | 4 – Low | 5 | AgentCash card, browser tab, social scrapers all render brand correctly
48 | 🟢 LOW — SEO & Brand | HelloSkip agent script integrated in RootLayout | ✅ Done | Apr 23 | 4 – Low | 1
49 | 🟢 LOW — Legal & Compliance | Legal entity rename: Relay Network, Inc. across footers, Privacy Policy | ✅ Done | Apr 24 | 4 – Low | 3 | README license footer updated
50 | 🟢 LOW — Legal & Compliance | Terms of Service + Privacy Policy PDF linked from site, settings, auth pages | ✅ Done | Mar 20 | 4 – Low | 4 | Download PDF button. /legal/ public path
51 | 🟢 LOW — Docs & Cleanup | Whitepaper + README updated (external agents, x402, MCP, Phase 1 completion) | ✅ Done | Mar–Apr | 4 – Low | 4 | STAKING_SPEC.md locked to v1. off-chain volume store documented
52 | 🟢 LOW — Docs & Cleanup | Remove dead /market page, dead components, legacy sdk/ directory | ✅ Done | Mar–Apr | 4 – Low | 3 | Build excludes OUTPUTS and relay-* sibling projects from tsc

## Weekly Breakdown
RELAY — WEEKLY COMMIT BREAKDOWN (Mar 19 – Apr 30, 2026)
WEEK | DATE RANGE | COMMITS | TOP THEMES | KEY SHIPPED
Week 1 | Mar 19–26 | ~80 | Plugin SDK, CLI, PoI validator, token factory, DAO | 8 registry plugins shipped; relay quickstart cmd; PoI scoring; bonding curve; legal pages
Week 2 | Mar 27 – Apr 3 | ~70 | Social engagement, multi-wallet, realtime contracts, auth | Autonomous LLM comment loop; Phantom/Solflare/Ledger/WalletConnect; SSR auth; RELAY mint on-chain
Week 3 | Apr 4–11 | ~30 | Solana Agent Kit, LCP/CLS perf, settlement bugfixes, env cleanup | plugin-autoagent; LCP Priority images; settlement buyer check; API key whitespace bug fix
Week 4 | Apr 12–21 | ~90 | x402 v1, on-chain reputation, agent profiles, escrow, admin panel | x402 Bazaar paywall; agent_profile PDA; relay_agent_profile program; outbound USDC tracking
Week 5 | Apr 22–28 | ~120 | Staking v1, execute_relay on-chain, marketplace redesign, Railway | Stake-gated register+relay; security test suite; terminal marketplace; Railway proxy; mobile UX
Week 6 | Apr 29–30 | ~190 | SDK v0.2, escrow hardening, x402scan discovery, brand identity | @relaynetwork/agent-sdk; ai-plugin.json; x402scan registered; RPC fallback; favicon/OG unified

## Stats
RELAY — 6-WEEK DELIVERY STATS
METRIC | VALUE | NOTES
Total commits (main branch) | 582 | Mar 19 – Apr 30
Production deployments | 100+ | All READY / GREEN
Items shipped (this checklist) | 52 | Grouped from 582 commits
Critical items | 10 | On-chain protocol + x402 economy
High-priority items | 13 | SDK, reputation, infra, marketplace
Medium-priority items | 19 | Tokens, plugins, social, contracts
Low-priority items | 10 | Perf, SEO, legal, docs
On-chain programs deployed | 3 | relay_agent_profile, relay_reputation, escrow
SDK versions shipped | 2 | v0.1.3 (@relaynetwork), v0.2.0 (@trace-relay)
x402 paid endpoints live | 3 | marketplace, feed/discover, protocol/stats
Security fixes | 5+ | Hardcoded secrets, PDA validation, sig checks
E2E test coverage | 44/44 passing | As of Mar 31